# SDN Platform — Status Report (Update)

Date: 24 March 2026
Prepared by: Appolica
Reporting period: Update since last report (23 March 2026)

# Executive Summary

Following our initial status report yesterday, we are pleased to share a significant update. Our team has continued working at full capacity over the past 24 hours, and we have now resolved 178 out of 254 items (70%), up from 148 (58%) reported yesterday.

Critical go-live items have seen substantial progress, with 92 of 117 critical items now resolved (79%), up from 70% yesterday. Non-critical items have also progressed, with 86 resolved (63%).

# Key Developments Today

A productive meeting was held between Brian, Sonja and Nikola today, resulting in several important clarifications and decisions:

Corporate & Academic Membership Flows — Resolved — The flows were reviewed in detail during the meeting, and it was confirmed that the current behaviour is working as expected. One additional flow was identified as missing and will be considered as part of Phase 2.

Awards Page — "Coming Soon" for Go Live — It was agreed that, for Go Live, the Awards page will display a "Coming soon" state, as further iteration is required and the current content is outdated.

Accreditation section fully complete — all 15 critical items resolved — up from 13 yesterday.

Knowledge Section fully complete — 8 of 9 critical items resolved, with the remaining 1 awaiting SDN content.

Membership — continued strong progress — multiple additional items completed following today's alignment meeting.

Non-critical items — an additional 21 non-critical items resolved since yesterday, demonstrating our continued commitment to platform quality beyond go-live requirements.

# Overall Progress

| Metric | Count | Percentage | Change vs Yesterday |
| --- | --- | --- | --- |
| Total items logged | 254 | — | — |
| Total resolved by Appolica | 178 | 70% | ↑ from 58% |
| Critical (Go-Live) items — Total | 117 | — | — |
| Critical (Go-Live) items — Resolved | 92 | 79% | ↑ from 70% |
| Critical (Go-Live) items — Remaining | 25 | 21% | ↓ from 30% |
| Non-critical items — Total | 137 | — | — |
| Non-critical items — Resolved | 86 | 63% | ↑ from 48% |

Note: Of the 25 remaining critical items, the majority are owned by SDN (content updates, copy changes, decisions) and are awaiting input from the SDN team.

# Progress by Feature Area

| Feature Area | Critical Total | Critical Resolved | Critical Remaining | Non-Critical Resolved | Status |
| --- | --- | --- | --- | --- | --- |
| Academy | 4 | 4 | 0 | 0 | Complete |
| Accreditation | 15 | 15 | 0 | 16 | Complete |
| Network | 1 | 1 | 0 | 6 | Complete |
| Award | 1 | 1 | 0 | 1 | Complete (Coming Soon) |
| About SDN Section | 3 | 3 | 0 | 5 | Complete |
| Case Studies | 2 | 2 | 0 | 4 | Complete |
| Knowledge Section | 9 | 8 | 1 | 10 | Nearly complete |
| Payments & Invoice | 7 | 6 | 1 | 0 | Nearly complete |
| Admin Panel | 5 | 4 | 1 | 0 | Nearly complete |
| Events & News | 6 | 5 | 1 | 6 | Nearly complete |
| Chapters | 3 | 2 | 1 | 3 | In progress |
| Membership | 56 | 38 | 18 | 28 | In progress (largest area) |
| Touchpoint | 5 | 3 | 2 | 7 | In progress |
| Total | 117 | 92 | 25 | 86 | — |

# Corporate & Academic Membership Flow — Resolved

Following today's meeting between Brian, Sonja and Nikola, the Corporate and Academic membership flows were reviewed in detail. It was confirmed that the current behaviour is working as expected.

One additional flow was identified as missing during the review. As agreed in the meeting, this will be addressed in Phase 2 — it does not impact Go Live readiness.

# Awards Page — "Coming Soon" for Go Live

It was agreed during today's meeting that the Awards page will display a "Coming soon" state for Go Live. The current content is outdated and requires further iteration, which will be addressed post-launch. This decision ensures the page does not present inaccurate information to users while allowing the team to focus on higher-priority items.

# Invoice Clarification — Follow-up

As communicated yesterday, Nikola has responded to Karin's email with a detailed explanation. The invoice referenced was a customer-generated document, not the platform's expected output. The system includes clear instructions for generating the correct invoice view. No platform changes are required.

# Go-Live Timeline & Dependencies

Current target: As noted in yesterday's update, our goal remains to complete and deliver all tasks assigned to Appolica by the end of tomorrow (Wednesday 26 March) for SDN testing. With 79% of critical items already resolved, we are confident in meeting this deadline.

To ensure alignment and timely progress towards Go Live, we need a confirmed timeline for the remaining items assigned to the SDN team, particularly those related to outstanding content and feedback. It would be important to have this clarified as soon as possible to avoid any impact on the delivery plan.

In summary:

Appolica deliverables: on track — 79% of critical items complete, target: end of day Wednesday 26 March.

SDN deliverables: blocking — confirmed timeline needed from SDN team to avoid delivery impact.

Corp/Academic flow (Item #58): resolved — current behaviour confirmed working. Additional flow deferred to Phase 2.

Awards page: "Coming soon" state agreed for Go Live — post-launch iteration planned.

# Next Steps

Complete all remaining Appolica items by end of day Wednesday 26 March — final push on Membership, Touchpoint, and remaining areas — ready for SDN testing.

Deploy all completed changes to production — 92 critical items and 86 non-critical items ready for release.

Implement "Coming soon" state for Awards page — as agreed in today's meeting.

Await confirmed timeline from SDN team — for remaining content, copy, and feedback items — critical to maintaining the Go Live schedule.

Should you have any questions or require further detail on any specific item, please do not hesitate to reach out. A detailed breakdown by feature area is available in the accompanying Excel report.

Kind regards,

Appolica Team